REQUEST FOR PROPOSALS: SOLAR ENGINEERING AND CONSTRUCTION SERVICES

# January 7, 2026

Detroit/Wayne County Port Authority 130 E. Atwater Street

Detroit, MI 48226

313-259-5091

The Detroit/Wayne County Port Authority (the Port Authority), a public corporation formed under Michigan’s Public Act 639 of 1978, is governed by a five-member board with appointments from the City of Detroit, Wayne County, and the State of Michigan. More information is available at portdetroit.com.

The Port Authority has been awarded a $21.9 million grant from the U.S. Environmental Protection Agency (EPA) under its Clean Ports Program to support the deployment of zero-emission equipment and infrastructure at the Port of Detroit. A key component is a ground-mounted photovoltaic (PV) solar array to offset energy used to charge industrial electric vehicle (EV) equipment at a partner terminal site. The grant period is January 1, 2025 through December 31, 2028.

To execute this project, the Port Authority seeks a qualified Design-Build Contractor, led by a Michigan-licensed Professional Engineer, to provide turnkey engineering, permitting, procurement, construction, commissioning, and performance verification of the PV system and its balance-of-system (BOS) components. This initiative supports the Port’s transition to clean energy, replacing diesel-powered equipment with battery-electric alternatives, improving air quality in communities such as Southwest Detroit and River Rouge, and creating good-paying union jobs through partnerships with local labor organizations.

The Detroit/Wayne County Port Authority invites proposals from qualified Design-Build Contractors to deliver a comprehensive solar energy solution at  Amrize Terminal. This project involves the design, permitting, procurement, construction, and commissioning of a photovoltaic (PV) solar array estimated at 316 kW to offset energy used for charging industrial electric vehicles (EVs). The overarching goal is to maximize energy offset for EV operations, reduce fossil fuel emissions, and ensure compliance with all federal and local requirements.

PROJECT OVERVIEW

The Port Authority plans to install a 1.0-acre solar array at the Amrize Terminal, with an estimated capacity of approximately 316 kW (PV). The final electrical output will be confirmed by the selected contractor based on the performance of the 1.0-acre array. The selected contractor will be responsible for engineering, permitting, construction, system integration, and commissioning to ensure successful start-up of the solar installation. The array will be designed to support charging of industrial electric equipment via Level 2 AC and DC Fast Chargers; however, charging equipment and EV units are not included in this RFP.

| Equipment | Quantity | Battery Capacity(1) | Charge Rate(1) | Expected Run Time |
| --- | --- | --- | --- | --- |
| Railcar Mover | 1 | 149 kWh(3) | 12 kW(2) | 4–8 hours |
| Large Forklifts | 2 | 60 kWh each | 10–25 kW | 6–8 hours |
| Mid-size Forklifts | 2 | 27 kWh each | 10–15 kW | 6–8 hours |
| Boom Lift | 1 | 20 kWh | 10–20 kW | 4–8 hours |
| Sweeper | 1 | 1.5–2 kWh | 1–2 kW | 4–8 hours |
| Gator | 1 | 12 kWh | 6–8 kW | 6–8 hours |
| Skid Steer | 1 | 72.6 kWh | 40–80 kW | 6–8 hours |

- Battery capacity and charging rate are estimated only. Final capacity and rates will be provided by the Owner representatives and documented prior to final design.

- Kilowatts = kW

- Kilowatt hours = kWh

The solar array will be designed to function by powering equipment on an as-needed basis via Level 2 and DC Fast Chargers (final charger specifications will be confirmed during the design phase). The solar array is not expected to produce more energy than what the site’s equipment and buildings use.  However, occasionally there will be days when the site is not operating, and the electricity will feed into the DTE Energy grid. Initial calculations indicate the solar array will produce enough power to charge equipment during even the lowest solar generating month (December); however, secondary power sources must be incorporated to ensure consistent energy availability during periods of low solar generation.

Site Background

The project will take place at 1301 Springwells Court in Detroit, Michigan, a waterfront industrial parcel situated along the Detroit River. This location offers unique operational advantages but also presents specific design and construction considerations. The property includes riparian rights extending to the USA–Canada International Boundary, subject to public navigation and avigation requirements. Its northwestern edge is defined by Springwells Court, a variable-width roadway, and portions of the site fall within a Limited Access Right-of-Way, which restricts ingress and egress.

The site also contains non-exclusive railroad spur easements, including T1 and T2 alignments, which serve Amrize. These easements occupy approximately 0.895 acres and must remain unobstructed throughout construction and operation. Any proposed solar infrastructure must be carefully planned to avoid encroachment into these corridors and maintain required clearances. In addition, the Contractor will be responsible for verifying all recorded easements and restrictions, which may include sewer, telecommunications, pipeline utilities, and dock access rights. Utility locates must be coordinated prior to any excavation. Survey control for the site is based on UTM Zone 17N (WGS84/NAD83 CORS96) in international feet, with an average combined scale factor of 0.99994826, ensuring precise layout and engineering accuracy.

Environmental Considerations

The site has known subsurface contamination and includes a felt barrier located approximately 12 inches below grade. Any disturbance to this barrier must be mitigated by replacement. Excavated soils may be stockpiled and reused where feasible; if reuse is not possible, soils must be tested and disposed of at a licensed landfill.

The Contractor’s construction plan should incorporate robust soil management protocols, health and safety measures, and stormwater controls to prevent discharge into the Detroit River. These environmental safeguards are critical to maintaining compliance and protecting surrounding ecosystems while advancing the Port Authority’s sustainability objectives.

Figure 1. Red box depicts approximate location of solar array. Specific location will be identified by selected Contractor.

Federal Crosscutting Requirements
This project is funded under the U.S. EPA Clean Ports Program and is subject to all applicable federal “Crosscutting” requirements. Crosscutting requirements refer to federal laws and regulations that apply across multiple programs and funding sources, ensuring compliance in areas such as environmental protection, civil rights, nondiscrimination, historic preservation, and other statutory obligations. Examples include the National Environmental Policy Act (NEPA), Endangered Species Act, Historic Preservation Act, and related provisions. The Contractor must ensure full compliance with these requirements throughout design and construction. Documentation confirming adherence will be required prior to contract award.

Proposal Summary

The Port Authority seeks proposals that deliver a cost-effective, high-performance solar energy solution aligned with the objectives outlined in this RFP. Respondents should demonstrate a clear understanding of the project’s technical requirements, site constraints, and environmental considerations while prioritizing value engineering to balance performance, sustainability, and cost. The selected Design-Build Contractor will be responsible for:

- Confirming system sizing: Validate that the proposed 1-acre PV array meets operational needs through a usage-based load analysis.

- Design and permitting: Prepare complete engineering plans, secure all necessary permits, and ensure compliance with federal, state, and local requirements.

- Integration and interconnection: Coordinate with DTE Energy for interconnection approval and integrate secondary power sources to supplement solar generation.

- Construction and commissioning: Deliver full construction services, including site preparation, installation, and system start-up, followed by performance verification.

Proposals must include a Lump Sum Fixed Fee (Stipulated Sum) covering all design-build services, permitting, environmental compliance, and commissioning of the solar array and balance-of-system components. This initiative represents a forward-thinking investment in clean energy infrastructure, supporting improved air quality, community health, and the Port Authority’s long-term sustainability goals. All proposals must adhere to the following requirements:

- Equal Opportunity Employer compliance

- Non-Collusion affidavit

- Build America, Buy America (BABA) compliance; Buy American preference when feasible

- Insurance: Builder’s Risk and Liability coverage with the Port Authority listed as additional insured

- Safety program submission and EMR disclosure

- Davis-Bacon prevailing wage compliance for all tiers of contractors

- Registration of all non-journey-level workers with a BAT-approved pre-apprenticeship program

- Workforce development commitments, including:

  - Registration of all non-journey-level workers in a U.S. Department of Labor BAT-approved registered apprenticeship program (pre-apprenticeship participation encouraged but not a substitute).

  - Performing all work under a Project Agreement with the Michigan Building and Construction Trades Council (MBCTC).

  - Requiring all contractors of any tier to execute a Letter of Assent to the Project Agreement prior to starting work.

  - Establishing non-traditional classifications (e.g., pre-apprentice, Summer Helper, Material Handler) to provide career and workforce development opportunities for individuals in the surrounding community.

DETAILED SCOPE OF SERVICES

The selected Design-Build Contractor will provide a turnkey solution for the solar energy system, covering all phases from concept through commissioning. These services include, but are not limited to:

- Preliminary Design & Recommendation

- Validate that the electrical output that will be provided by a 1.0 acre solar array. Confirm this output will meet EV charging requirements through a detailed usage-based load analysis.

- Coordinate with other project consultants as necessary to confirm interface and interconnection requirements.

- Recommend the most cost-effective and operationally feasible design solution.

- Engineering & Final Design

- Prepare stamped civil, structural, and electrical drawings and calculations by a Michigan-licensed Professional Engineer.

- Permitting & Regulatory Compliance

- Ensure compliance with NEC, IBC, local codes, and DTE Energy interconnection requirements.

- Use only materials listed, tested, and labeled by Underwriters Laboratories (UL), Factory Manual (FM), Electrical Testing Laboratories (ETL), or another nationally recognized testing laboratory.

- Secure all necessary permits for construction and interconnection.

- Provide documentation that all applicable federal grant requirements are satisfied, including Build America, Buy America (BABA) compliance/waiver requirements, Davis-Bacon Act requirements, and other applicable grant conditions.

- Procurement

Prioritize recyclable, recycled, and ENERGY STAR® rated materials where available. Procure all equipment and materials required for the solar array and associated systems, meeting the following standards or equivalent:

- PV Modules: UL-listed, monocrystalline, anti-corrosion frames, high wind tolerance, minimum 90% of specified power at purchase, and 25-year performance warranty (≥80% of original power).

- Inverters: UL 1741 and IEEE 1547 listed, peak efficiency ≥96%, operational indicators, built-in data acquisition, shaded outdoor mounting, and minimum 10-year warranty.

- Performance Monitoring System: Rapid notification time for system irregularities and networking equipment, engineering, programming, wiring, and software to allow remote connection.

- Construction & Installation

- Perform full construction services: site preparation, foundation work, PV module and inverter installation, trenching, conduit, grounding, and commissioning.

- Project Management & Coordination

- Attend biweekly coordination meetings with the Port Authority, Owner’s Representative, and Amrize representative.

- Manage all subcontractors and construction personnel.

- Develop and maintain a detailed project schedule, including the critical path to ensure timely delivery.

- Maintain cost controls at all project stages for on-time and on-budget project delivery.

- Documentation & Quality Assurance

- Review and approve all shop drawings prior to submission.

- Prepare construction drawings, punch lists, and supervise warranty work.

- Deliver stamped as-built documents from a Michigan-licensed Professional Engineer.

- Workforce and Labor Compliance

- Perform all work under a Project Agreement with the Michigan Building and Construction Trades Council (MBCTC).

- Require all contractors of any tier to execute a Letter of Assent to the Project Agreement prior to starting work.

- Ensure Davis-Bacon prevailing wage compliance for all tiers of contractors.

- Register all non-journey-level workers in a U.S. Department of Labor BAT-approved registered pre-apprenticeship program.

- Ongoing Collaboration

- Maintain day-to-day coordination with the Port Authority and project stakeholders.

- Ensure all decisions align with project goals, budget, and schedule.

Important Note: The selected Contractor will not procure EV equipment or chargers. Electrical connections between the solar array and EV chargers will be designed under a separate contract. Coordination with that engineer is required to ensure system compatibility.

This scope reflects the Port Authority’s commitment to a high-performance, cost-effective solar solution that advances sustainability, operational reliability, and environmental stewardship.

RFP PROCESS AND REQUIREMENTS

- Open RFP. This RFP is open to any qualified firm or individual with demonstrated experience in design-build delivery for solar energy systems.

- Competitive Procurement Process. The Grant agreement and corresponding federal regulations require that all procurement for materials and services be in compliance with federal procurement standards set forth in 2 CFR Sections 200.317 thru 200.327, which, among other things, require competitive processes, prohibition of conflicts of interest, non-discrimination, equal opportunity, and the inclusion of certain provisions in the award of contracts, as provided in Appendix II to 2 CFR part 200. The Port Authority incorporates by reference all the requirements in 2 CFR Sections 200.317 through 200.327 and Appendix II to 2 CFE Part 200.

- Site Visit. One site visit will be scheduled during the RFP process. Details will be provided via email and posted on the Port Authority website. The site visit is tentatively scheduled for January 12, 2026.

- Pre-Bid Communication. Interested bidders must register by emailing rfp@portdetroit.com. Registered firms will receive supplemental site files in CADD format.

  - Questions must be submitted by January 20, 2026, 5:00 PM ET.

  - Responses will be issued via addenda to all registered bidders.

  - Direct contact with Port Authority staff outside this process is prohibited.

  - Supplemental files must be destroyed by February 1, 2026 and cannot be shared with third parties.

- Submission. Proposals in response to the RFP are due no later than 5 p.m. January 30, 2026. Late submissions will not be considered. Please submit only ELECTRONIC responses to the following email address: rfp@portdetroit.com. Each submission should include the following sections:

  - Firm Information

    - Name, address, phone number, and primary contact

    - Brief history of the organization, business entity type, and corporate officers

  - Relevant Experience

    - Summary of similar projects completed within the past five years

    - Include scope, cost, client name, delivery date, and contact information

  - Project Team

    - Identify key personnel, roles, and time commitment

    - Provide resumes and indicate on-site or off-site presence

    - Demonstration of compliance with workforce and labor compliance requirements

  - References

    - Minimum of three client references for similar projects (two within the past five years)

  - Services and Approach

    - Describe your scope of pre-construction and construction services. Include:

      - Self-Performed Work: List trades and clarify supervision cost inclusion

      - Subcontractors: List proposed subcontractors and markup rates

  - Project Execution Strategy

    - Outline approach to design, permitting, procurement, and construction

    - Address logistics, scheduling, quality assurance, and cost control

  - Compliance and Safety

    - Confirm Build America, Buy America (BABA) compliance or waiver

    - Confirm that all contractors at any tier will pay the current Davis-Bacon Prevailing Wage rate for all crafts performing work on the project

    - Confirm that all non-journey level workers will be registered with a BAT-approved apprenticeship program

    - Provide insurance certificates, safety program details, and EMR disclosure

  - Cost Proposal

    - Submit a Lump Sum Fixed Fee (Stipulated Sum) covering all required services

  - Schedule

    - Provide a proposed timeline and schedule control method (e.g., Gantt chart)

  - Warranties

    - Provide industry-standard warranties for all equipment and services

- Negotiations. The Owner does not anticipate prolonged negotiations with the selected vendor. All bidders must submit their best and final offer at the time of bid submission.

- Additional Information. The Port Authority reserves the right to request additional information or clarification from firms, conduct interviews, and negotiate terms prior to making a final selection. This RFP does not constitute a commitment by the Port Authority to award a contract.

## Disclaimers. The Port Authority reserves the right to reject any or all responses to this RFP and to waive any informalities or irregularities in the submission process. All materials submitted in response to this RFP become the property of the Port Authority and may be subject to public disclosure. The Port Authority assumes no liability to any person or entity for the costs incurred in responding to this RFP.

- Schedule

  - RFP Issued: January 7, 2026

    - Site Visit: January 12, 2026 (tentative)

    - Questions Due: 5pm January 20, 2026

    - Q&A Posted: 5pm January 26, 2026

    - Proposal Due: 5pm January 30, 2026

- Evaluation Criteria. Proposals will be evaluated per the following criteria:

- Qualifications and experience with similar projects

- Technical approach and value engineering

- Project schedule and ability to meet deadlines

- Cost proposal and price realism

- Compliance with BABA, Davis-Bacon and other wage requirements, and safety requirements

- Past performance and references

SUPPLEMENTAL GENERAL CONDITIONS

DEFINITIONS The word “Buyer” means the Port Authority identified as the “Bill To” entity on the face of this purchase order.  The word “goods” as used herein shall mean, without limitation, the products, articles, services, materials and/or equipment described on the face hereof. The term “Customer” refers to the Customer of the Buyer, who may be the end user of the goods.  All references to Buyer in this Agreement will be deemed to be references only to the Port Authority identified as “Buyer” herein.  Seller acknowledges that Buyer will be solely responsible for its own obligations and performance under any purchase order or other agreement entered into under these terms and Seller will look solely to Buyer with respect to rights and remedies under this Agreement.

ACCEPTANCE The first to occur of Seller’s acceptance of this Order or shipment of goods pursuant to this Order shall constitute Seller’s agreement to the terms and conditions set forth on the face and the back of this Purchase Order.  No other terms, whether or not contained in any bid, estimate, acknowledgement, agreement confirmation or invoice given by Seller, shall in any way modify or supersede any of the terms of this Order or otherwise be binding on Buyer, and Buyer hereby explicitly rejects all such other terms unless it has accepted such other terms by a written instrument signed by its authorized representative.

QUALITY Seller warrants that all goods will conform to specifications furnished by Seller and approved by Buyer or furnished by Buyer.  Seller acknowledges the receipt of a copy of all such specifications furnished by Buyer.  Seller warrants that all goods have been tested for their safety, will be of merchantable quality and of good material and workmanship, free from defect and suitable for their intended use.  If applicable, Seller will assign to Buyer all warranties applicable to any portion of the goods obtained by Seller from third parties, or if not assignable, will assert such warranties on behalf of Buyer at Buyer’s request. Seller warrants that the goods shall comply with all applicable federal, state, and local laws, statutes, rules and regulations.  In the event that Seller becomes aware or has reason to believe that a condition exists, within the manufacturing facility or goods themselves, which does or may adversely impact any of the above warranties, Seller shall promptly notify Buyer of same.  All deliveries of goods to countries outside the United States shall conform to and comply in every respect to the provisions of the laws and regulations of the countries into which the goods are delivered and countries where the goods will be used (provided Buyer has advised Seller which countries are involved), to the extent such laws and regulations are applicable to such goods.

REJECTION Payment for goods delivered hereunder shall not constitute acceptance thereof.  Buyer reserves the right to inspect and test such goods and to reject, and return to Seller at Seller’s expense, goods (a) delivered in excess of the quantity ordered, (b) which do not conform to specifications or are defective, or (c) which in any way violate applicable law.  Buyer’s failure to inspect goods prior to use shall not constitute acceptance of such goods, regardless of the passage of a reasonable period of time.  Buyer, at its option may require replacement of defective or rejected goods or a refund of the purchase price as well as payment of damages.  Nothing contained in the Order shall relieve the Seller in any way from the obligation of testing, inspection, and quality control.

PRICES Seller warrants that prices shown on this Order shall be complete, and no additional charges of any type (e.g., shipping, packaging, labeling, custom duties, taxes, etc.) shall be added or borne by Buyer without its expressed written consent.  Any cash discount periods will be calculated from receipt of invoice or receipt of acceptable goods, whichever occurs later.  On invoices returned for correction, the cash discount period will be calculated from receipt of the corrected invoice.

SHIPPING terms apply only to material procurement under the design-build contract and do not alter the Contractor’s obligation to provide full turnkey services, including installation and commissioning.

DELIVERY Time is of the essence of this Order, and if delivery of goods is not completed by the time promised, Buyer reserves the right, without liability and in addition to other rights and remedies, to: (i) Terminate this Order by notice effective when received by Seller as to goods not yet shipped; (ii) Purchase substitute items; and/or, (iii) Charge Seller with any loss incurred.

TERMINATION The Port Authority may terminate this contract, in whole or in part, for convenience or for cause. Upon receipt of termination notice, the Contractor shall immediately stop work and ensure all subcontractors cease work. Termination without cause will be subject to applicable federal grant requirements, including documentation and compliance with 2 CFR Part 200. In the event of termination for cause due to default, failure to meet contract terms, or failure to provide adequate assurances of performance, the Port Authority shall not be liable for any damages sustained by the Contractor and retains all rights and remedies provided by law and equity.

GRANT REVOCATION Seller acknowledges that Buyer is a grantee under the EPA Clean Ports program (the “Grant”) and that the purchase hereunder, and that continuation of this agreement is contingent upon the availability of Grant funds. In the event that funding under the Grant is revoked, withdrawn, or otherwise rendered unavailable for any reason, the purchaser may terminate this contract immediately and shall not be liable for any further payment or obligation, claims for damages, compensation, or reimbursement.

CHANGES Buyer shall have the right at any time to make changes in drawings, designs, specifications, materials, packaging, time and place of delivery and method of transportation.  If any changes cause an increase or decrease in the cost or the time required for performance of this Order, an equitable adjustment shall be made and this Order shall be modified in writing accordingly.

CONFIDENTIALITY Seller shall consider all information furnished by Buyer, including the existence of this Order, to be confidential and shall not disclose any such information to any other person, or use such information itself for any purpose other than performing this Order, unless Seller obtains written permission from Buyer.  Upon the termination of this Agreement, or upon Buyer’s request, Seller agrees promptly to return to Buyer all documentation or other tangible materials containing and/or embodying any of the Information (including, without limitation, all copies, reproductions, summaries and notes of the contents thereof), and to certify that all such Information has been returned to Buyer or disposed of in a manner approved by Buyer.

FORCE MAJEURE Each party will be excused from performance under this Agreement while and to the extent that it is unable to perform, for a cause beyond its reasonable control. Force majeure will not include labor shortages or work stoppages. If either party is rendered unable wholly or in part by force majeure to carry out its obligations under this Agreement, then the party affected by force majeure will give written notice with explanation to the other party immediately. The affected obligations of the party giving notice will be suspended only during the continuance of the events giving rise to the force majeure provided that the affected party is acting with due diligence to remedy the delay caused by the force majeure. If Seller is unable to perform for a period of more than fifteen (15) business days due to any force majeure event, Buyer may terminate this Agreement.

INFRINGEMENT Seller warrants that the goods and/or their use, sale and/or consumption, pursuant to this Order do not and will not infringe any patent, trademark, copyright, or other intellectual property right and there is no unauthorized use of proprietary rights of another party.  Seller agrees, upon receipt of notification, to promptly assume all responsibility for defense of any suit or proceeding which may be brought against Buyer or its agents, customers or vendors for alleged intellectual property infringement and/or alleged unfair competition resulting from similarity in design, trademark or appearance of goods furnished hereunder, and Seller further agrees to indemnify Buyer, its agents, vendors and customers against any and all expenses, losses, royalties, profits and damages, including court and/or settlement costs and attorneys’ fees resulting from any such suit or proceeding.

INDEMNIFICATION/INSURANCE Seller shall defend, indemnify and hold Buyer harmless against all damages, claims, liabilities and/or expenses (including attorneys’ fees) arising out of or resulting in any way from any defect in the goods purchased hereunder, from any wrongful act or omission of Seller, its employees, agents or subcontractors, or from Seller’s breach of any warranty as provided herein or otherwise provided by law.  Seller shall maintain comprehensive liability insurance, including products liability coverage, contractual liability and broad form vendor’s endorsements covering Seller’s obligations under this Order, such insurance to have aggregate limits of at least five million dollars ($5,000,000), and to be with an insurance carrier reasonably satisfactory to Buyer.  Seller shall furnish certificates of insurance evidencing such coverage to Buyer at Buyer’s request.

INSPECTION RIGHTS Upon reasonable notice to Seller, Buyer or Buyer’s independent service may inspect Seller’s plants where goods are manufactured. In accordance with Buyer’s Inspection Rights, as it pertains to the goods or services ordered herein, Buyer or Buyer’s client’s review or inspection of the goods or services ordered under this Purchase Order, either by physical examination or review of drawing or technical documents, do not constitute acceptance nor shall such review or acceptance affect or release any of Seller’s obligations with respect to the ordered goods or services.

DISPUTE RESOLUTION Any dispute between the parties relating to this Agreement or the breach thereof shall be resolved by binding arbitration in Detroit, Michigan, pursuant to the Commercial Arbitration Rules then obtaining of the American Arbitration Association.  The arbitrator(s) shall have no power to add to or modify the terms of this Agreement.  Judgment on the award rendered by the arbitrator(s) may be entered in any court having jurisdiction thereof.  The arbitrator(s) shall apply the substantive law of Michigan except that the interpretation and enforcement of this arbitration provision shall be governed by the Federal Arbitration Act.  The arbitrator(s) shall not award either party punitive damages, and the parties shall be deemed to have waived any right to such damages.  The proceedings shall be confidential and the arbitrator shall issue appropriate protective orders to safeguard both parties’ confidential information.  The fees of the arbitrator and the American Arbitration Association shall be split equally between the parties.

ASSIGNMENT No part of this Order may be assigned or contracted by Seller without the prior written approval of Buyer.  With the consent of Seller, which shall not be unreasonably withheld, Buyer may, at its option, either terminate or assign a portion or all of this Order in the event of a sale, transfer, or other disposition of any operating unit or business of Buyer participating in this Order, provided that such termination or assignment shall relate only to the requirements of such operating unit or business.  In the event of assignment, Seller agrees that Buyer shall have no further obligations with respect to the assigned portion of the Order after the date of such assignment.

WARRANTY ASSIGNMENT It is understood that Buyer is purchasing goods for the purpose of resale to Buyer’s Customer.  Accordingly, all warranties provided by the Seller or other third parties under this agreement shall be transferable to Buyer’s Customer.  If requested by Buyer, Seller will assist in transferring warranty/warranties to Buyer’s Customer.

SETOFFS All claims for money due or to become due from Buyer shall be subject to deduction or setoff by the Buyer by reason of any counterclaim arising out of this or any other transaction with Seller.

WAIVER Buyer’s failure to insist on performance of any terms or conditions herein or to exercise any right or privilege or Buyer’s waiver of any breach hereunder shall not thereafter waive any other terms, conditions or privileges, whether of the same or similar type.

GOVERNMENTAL REGULATIONS Seller’s obligations hereunder shall be subject to and comply with all applicable governmental laws, rules, regulations, and executive orders, including but not limited to Equal Opportunity/Affirmative Action clauses contained in Executive Order 11246 (60-1.4(a)), as amended, 41 CFR 60-300.5(a) (Veterans) and 41 CFR 60-741.5 (Rehabilitation Act), which requires a written Affirmative Action Plan, annual EEO-1 and Vets-100 reports, and adherence to all relevant rules, regulations and orders of the Secretary of Labor.

INDEPENDENT CONTRACTOR The Contractor shall, at all times, act as an independent contractor and not as an employee or agent of the Port Authority. Nothing in this agreement shall create an employer-employee relationship. Notwithstanding independent contractor status, the Contractor and all subcontractors must comply with Davis-Bacon prevailing wage requirements and ensure that all non-journey-level workers are registered with a BAT-approved apprenticeship program, as required by the RFP.

GOVERNING LAW This Order shall be governed and constructed by the substantive federal and state law of the state of Michigan as it applies to contracts made and to be performed wholly within such state.

ENTIRE AGREEMENT This Order, and any documents referred to on the face hereof, constitutes the entire agreement of the parties.

TOTAL COST is not to exceed the price listed on this purchase order without prior written authorization as evidenced by issuance of a written change order by Buyer.

INVOICES Invoice timelines will align with agreed-upon payment terms in the final contract and applicable federal grant requirements. The 45-day limitation will not apply where milestone-based or federally mandated payment schedules are in effect.

CLOSING STATEMENT

The Port Authority appreciates your interest in providing services and your efforts in submitting a proposal.

Respectfully,

Mark Schrupp Executive Director

Detroit/Wayne County Port Authority 130 E. Atwater St.

Detroit, MI 48226 mschrupp@portdetroit.com